## Basic Gantt Chart
Night Strider Gantt Chart
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS)
Snapshot 2
| Write Beginning Character Controller | 2021-02-22 | 2021-03-14 | 0 | 21
| Create Test Level | 2021-02-22 | 2021-02-26 | 0 | 5
| Create Basic Player Assets | 2021-02-26 | 2021-03-01 | 4 | 4
| Make Test Pieces for Level Generator | 2021-03-01 | 2021-03-03 | 7 | 3
| Research Procedural Generation | 2021-03-04 | 2021-03-11 | 10 | 8
| Create Starter Level Generator | 2021-03-05 | 2021-03-14 | 11 | 10
Snapshot 3
| Develop Character Controller Further | 2021-03-15 | 2021-03-26 | 21 | 12
| Block Out Level Chunks | 2021-03-15 | 2021-03-22 | 21 | 8
| Test Procedural Generation | 2021-03-20 | 2021-03-26 | 26 | 7
| Create Some Environment Assets | 2021-03-23 | 2021-03-26 | 29 | 4
Snapshot 4
| Implement Upgrade System | 2021-03-27 | 2021-04-09 | 33 | 14
| Create Full Level Chunks | 2021-03-27 | 2021-04-03 | 33 | 8
| Create Enemy AI | 2021-04-02 | 2021-04-09 | 39 | 8
| Import Enemy Assets | 2021-04-07 | 2021-04-09 | 44 | 3
| Implement Level Progression | 2021-04-07 | 2021-04-09 | 44 | 3
Final Sprint
| Create In-Game UI | 2021-04-10 | 2021-04-13 | 47 | 4
| Polish Character Controller | 2021-04-13 | 2021-04-20 | 50 | 8
| Create Menus | 2021-04-17 | 2021-04-20 | 54 | 4
| Polish Assets | 2021-04-20 | 2021-04-28 | 57 | 9
| Add Game Start and End Sequences | 2021-04-23 | 2021-04-28 | 60 | 6
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1